## Sheet1
ISSUES-02
Rule | Line | Contract | Function | Severity | Comment | Assigned To | Adjusted | Comments
Unauthoried access |  | Ownable | transferOwnership() | 3 | transferOwnership function is restricted by onlyImmediateOwnerOrWhitelisted modifier. It means that every whitelisted account can become an owner. | ALEX | yes
Bug | 107 | RBACData | unVerifyUser | 2 | It is not checked whether _operator argument is verified already. Check verified operators count. Moreover, if this check (line 94) remains for users verificatin, this check for unverification is redundant. | ALEX | no
Bug | 94 | RBACData | verifyUser | 2 | It is not checked whether _operator argument is verified already. | ALEX | no | Needs further discussion from a business logic perspective
Code logic | 36-42 | Entity |  | 2 | There are no restrictions in liking/disliking functionality. Needs to be removed |  | no | Needs further discussion from a business logic perspective
Code/project architecture |  | AssetBallot |  | 2 | AssetBallot contract keeps the address of assetToken, however the voting logic is implemented it the AssetToken contract itself. So, the use case for this contract is unclear. | ALEX | yes | Contract has been removed
Code logic | 96 | AssetWhitelist | allowTransaction | 2 | If all flags are switched off and whitelist is enabled then the function will always return true. However, it should return false. Thus, we recommend adding the last return true; statement inside the last if-block. In case all the flags are switched off the function will return false (dafault bool value). Function code needs cleaning. |  | no
Code logic violation |  | AssetWhitelist | removeCountry() | 2 | indexOfCountries is not changed, however the index of last country is changed. Index of deleted country is not deleted. We recommend using allowedCountries.pop() instead of allowedCountries.length-- in order to increase code readability and reduce gas costs. In addition, if (index == allowedCountries.length-1) then the code is redundant. We recommend considering this particular case separately. |  | no
Code logic violation | 54 | Sudo |  | 2 | tempAddr state variable corresponds to the latest request only. Since that, it may be overwritten by the second request before the first one is confirmed. In that case, after the confirmation of the former request address from the latter request will be removed from Sudo group. | ALEX | yes
Code logic violation | 125 | KycProcessTracker | updateCustomerStorageAddr | 2 | After changing storageAddr it should be checked whether the old one was previously whitelisted. If so, the old one should be unwhitelisted and the new one should be whitelisted. In addition, there may appear some issues if different users use the same starageAddr. | ALEX | not applicable
Incomplete code |  | Everywhere |  | 2 | A lot of TODO's across all the code. |  | no
Missing checks |  | Asset | createAssetToken | 2 | this function shouldn't be called after createFeeManager, createWhitelist, and others, since it overwrites assetToken address. |  | no | Needs further discussion from a business logic perspective
Overpowered role | 102-116 | AssetWhitelist |  | 2 | Setters with onlyAdmin modifier provide too much powers to admins. |  | no
Overpowered role | 116-136 | KycProcessTracker |  | 2 | updateCustomerStatus(), updateCustomerStorageAddr(), updateDocumentStatus() functions provide too much powers to admins. Moreover, transactions may be censored using updateDocSubmissionCost() function and front-running. | ALEX | not applicable
Overpowered role | 76 | AssetRankTracker | setRank | 2 | Transactions may be censored by changing the limits and using front-running. |  | no
Overpowered role | 50-62 | Ticker |  | 2 | Owner can immediately chagne rates at will. |  | no | Needs further discussion from a business logic perspective
Overpowered role |  | Asset | setMinTokenPercentage | 2 | Sudo user can immediately change minTokenPercentage state variable at will. |  | no
Code logic |  | CyclicPausable | isNotLastCycle() | 2 | The modifier works incorrectly in case maxCycles == 0, returns false instead of true. | ALEX | not applicable
Code logic | 97 | Claimer | hasEnoughPlatformTokens | 1 | Consider changing visibility modifier of hasEnoughPlatformTokens() function to internal since after some claims it will return inconsistent info. |  | no
Redundant code |  | TimePausable | enableTimeValidation, disableTimeValidation | 1 | Unused functions. | ALEX | not applicable | Needs further discussion from a business logic perspective
Unchecked access |  | Claimer | claimerFunded() | 1 | Has no restrictions; can be called multiple times. |  | no
Digital signature misuse | 67 | KycProcessTracker | submitDocumentDigestAndSignature | 1 | At the same time, this check seems redundant as msg.sender can always get the signature of function arguments. | ALEX | no | maxCycles = 0 has a very specific purpose
Bug | 94 | Multisignature |  | 1 | We recommend replacing lines 93-94 with pendingMultisigTransactions.pop() statement. | ALEX | yes | Contract has been removed
Code logic / Redundant code | 37 | KycProcessTracker | constructor | 1 | tradersGroup is saved as a variable of Trader type. However, in Groups contract the same address is already saved in traderAccCtrl state variable (with another type). | ALEX | yes
Code readability | 47 | Ticker |  | 1 | Replace * 60 with * 1 minutes. |  | no
Code readability | 27 | TickerDecentralized |  | 1 | Replace * 60 with minutes. |  | no
Code style | 14 | Roles |  | 1 | verified_bearer must be in mixedCase. | ALEX | yes
Code style | 19 | Multisignature |  | 1 | signatureCount variable is of uint8 type, however the number of this group members may be larger. | ALEX | yes | Contract has been removed
Code style | 59 | Multisignature |  | 1 | Consider using bool type instead of uint8. | ALEX | yes | Contract has been removed
Code style | 26-27 | TickerDecentralized |  | 1 | Variables can be marked as constant. |  | no
Costly loop | 83-89 | Multisignature |  | 1 | Replace the executed transaction with the last one in pendingMultisigTransactions array instead of moving all the transactions. | ALEX | yes | Contract has been removed
Deviation from ERC20 standard | 16 | PlatformToken |  | 1 | Decimals variable shoul be of uint8 type. |  | no
Deviation from ERC20 standard |  | PlatformToken | transfer() | 1 | The function SHOULD throw if the message caller’s account balance does not have enough tokens to spend. |  | no
Deviation from ERC20 standard | 37 | PlatformToken |  | 1 | balances[msg.sender] = totalTokens; Should trigger Transfer(0,msg.sender, totalTokens) event. |  | no
Deviation from ERC20 standard | 25 | BaseAssetToken |  | 1 | Decimals variable shoul be of uint8 type. |  | no
Deviation from ERC20 standard | 94 | BaseAssetToken |  | 1 | balances[_owner] = totalTokens; Should trigger Transfer(0,msg.sender, totalTokens) event. |  | no
Deviation from ERC20 standard |  | BaseAssetToken | transfer() | 1 | The function SHOULD throw if the message caller’s account balance does not have enough tokens to spend. |  | no
Gas optimisation | 72-76 | IndexedEntities | addItem | 1 | items[_owner][_type].count should be placed in local variable as it is read 3 times. This will reduce gas consumption. | ALEX | yes | Contract has been removed
Interfaces are contracts |  | Everywhere |  | 1 | All contracts with names starting with "I..." should be declared as interfaces. |  | no
Vote logic |  | AssetBallot | sellAssetVote() | 1 | There is no effect in voting to keep the asset. |  | yes | Contract has been removed
Misleading comment | 93 | BaseAssetToken |  | 1 | Not deployer but _owner. |  | no
Misleading comment | 144 | Asset |  | 1 | whitelist -> FeeManager. |  | no
Misleading comment | 157 | Asset |  | 1 | deployed -> set. |  | no
Misleading names | 23 | AssetBallot |  | 1 | minOwnershipPercentage is not persentage but amount. |  | yes | Contract has been removed
Misleading names | 13 | AssetToken |  | 1 | minOwnershipPercentage is not persentage but amount. |  | no
Misleading names |  | Groups | onlyAdmins, onlyAgents | 1 | should be added "verified". | ALEX | yes
Misleading names |  | AccessControl | onlyAdmins | 1 | should be added "verified". |  | yes
Misleading NatSpec | 147 | AssetBallot |  | 1 | Copy-paste from comment above. |  | yes | Contract has been removed
Misleading NatSpec | 52 | AssetWhitelist |  | 1 | Copy-paste from comment above (@param). |  | no
Misleading NatSpec | 21 | AssetRankTrackerFactory |  | 1 | Copy-pasted from AssetFactory contract. |  | no
Misleading NatSpec | 28-30 | Fee |  | 1 | Copy-paste. |  | no
No private data |  | IndexedEntities | getItem, getCount, hasItem | 1 | There is no effect in restricting access in getter functions since all the data is public on blockchain. | ALEX | yes | Contract has been removed
No private data |  | RBACData | много где | 1 | There is no effect in restricting access in getter functions since all the data is public on blockchain. | ALEX | not applicable
Overpowered role | 34 | Registry |  | 1 | All the critical addresses of the system can be replaced, thus the functionality can be changed at will. |  | no
Redundant code | 20-22 | TimePausable |  | 1 | Initial values do not need to be overwritten. | ALEX | yes
Redundant code | 74-78 | AssetBallot |  | 1 | Initial values do not need to be overwritten. | ALEX | yes | Contract has been removed
Redundant code |  | AssetBallot | keepAssetVote | 1 | There is no effect in voting for keeping the asset. | ALEX | yes | Contract has been removed
Redundant code |  | AssetBallot |  | 1 | This contract is unused. | ALEX | yes | Contract has been removed
Redundant code | 27 | PlatformToken |  | 1 | Change allowed mapping visibility to internal in order to save on gas at the deployment. |  | no
Redundant code | 23 | PlatformToken |  | 1 | Change balances mapping visibility to internal in order to save on gas at the deployment. |  | no
Redundant code | 35 | BaseAssetToken |  | 1 | Change allowed mapping visibility to internal in order to save on gas at the deployment. |  | no
Redundant code |  | BaseAssetToken | getName(), getSymbol() | 1 | getName() and getSymbol() are redundant as name and symbol variables have public visibility level. |  | no
Redundant code | 125, 143 | BaseAssetToken |  | 1 | withinLifespan modifier is redundant -- included in whileIsInUpperWave modifier. |  | no
Redundant code | 23 | BaseAssetToken |  | 1 | Change balances mapping visibility to internal in order to save on gas at the deployment. |  | no
Redundant code | 73 | BaseAssetToken |  | 1 | _minOwnershipPercentage constructor argument is unused. The require check should be placed in AssetToken contract constructor. |  | no
Redundant code | 66-69 | AssetToken |  | 1 | Initial values do not need to be overwritten. |  | no
Redundant code | 107 | AssetToken | voteForKeepingTheAsset | 1 | There is no effect in voting for keeping the asset. |  | no
Redundant code | 27 | Multisignature |  | 1 |  | ALEX | yes | Contract has been removed
Redundant code | 27-28 | KycProcessTracker |  | 1 | Initial values do not need to be overwritten. | ALEX | yes
Redundant code | 108 | KycProcessTracker |  | 1 | This should be done only if customer[_addr].storageAddr is non-zero. | ALEX | yes
Redundant code | 11 | RankTracker | constructor | 1 | The same check is applied in the constructor of Groups contract. |  | no
Redundant code | 60 | AssetRankTracker | constructor | 1 | The same check is applied in the constructor of Groups contract. |  | no
Redundant code | 26 | Entity | constructor | 1 | The same check is applied in the constructor of Groups contract. |  | no
Redundant code | 48 | Asset |  | 1 | owner variable is defined in Entity contract, its value will be rewritten with zero. This variable is unused. |  | no
Redundant code | 73-91 | FeeManager | createDefaultFees | 1 | asset token address should be placed in memory variable instead of 5 external calls. |  | no
Redundant code | 37 | FeeManager |  | 1 | Initial values do not need to be overwritten. |  | no
Redundant code | 89-129 | Ticker |  | 1 | Remove all unused functions. |  | no
Redundant code | 57 | Claimer |  | 1 | Initial values do not need to be overwritten. |  | no
Redundant code | 47 | BEE |  | 1 | Initial values do not need to be overwritten. |  | no
Use enum | 56-59 | Asset |  | 1 | We recommend using enums for variables with finite number of values (`state`) to increase code readability. |  | no
Visibility | 29 | BaseAssetToken |  | 1 | owner state variable has no visibility modifier. In case the visibility modifier is set to public, getOwner() getter function will be redundant. |  | no
Visibility | 21-22 | Entity |  | 1 | We recommend setting internal visibility level. |  | no
|  | CyclicPausable |  | 1 | `onlyIfActivated onlyIfDeltaHasExpired` can be replaced by just `onlyIfDeltaHasExpired` modifier call | ALEX | no | necessary to take a deeper look at the implications
Redundant code |  | Ownable | onlyWhitelisted() | 1 | The modifier is unused. | ALEX | yes
Redundant code |  | BaseAssetToken | onlyOwner | 1 | The contract is ownable, thus it includes immediateOwner variable. |  | no | mmmmm….
Typo | 42 | KycProcessTracker |  | 0 | Submitts -> Submits | ALEX | yes
Deployment script |  | KycProcessTracker |  | 0 | KycProcessTracker contract should be added to the admins group in Registry contract in deploy script, otherwise it will not be able to update whitelist contract. | ALEX | no